## Bid Summary
UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING
UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING | UPWORK BID ESTIMATE — SYSLOG-NG CENTRALIZED LOGGING
Editable estimate for scope, effort, cost, milestones, risks and acceptance
PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION | PROJECT INFORMATION
Project | Syslog-ng implementation on Red Hat Enterprise Linux
Prepared by | Muhammad Khalid Khan
Bid model | Fixed price calculated from estimated hours
Recommended package | Production Standard
Estimate validity | 14 calendar days
BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE | BID AT A GLANCE
TOTAL HOURS |  | WORKING DAYS |  | PROPOSED BID |  | CONTINGENCY
80 |  | 10 |  | 3550 |  | 10%
DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED | DELIVERABLES INCLUDED
1 | Install and validate syslog-ng on RHEL | [5 empty] | Included
2 | Configure approved TCP/UDP listening ports | [5 empty] | Included
3 | Store logs by listening port, source IP and date | [5 empty] | Included
4 | Rotate, compress and archive logs by policy | [5 empty] | Included
5 | Delete expired archives using tested retention rules | [5 empty] | Included
6 | Build graphical monitoring dashboard and source-down alerts | [5 empty] | Included
7 | Track source IP, port and last-received timestamp | [5 empty] | Included
8 | Testing, documentation and knowledge-transfer session | [5 empty] | Included
RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE | RECOMMENDED BID NOTE
Submit the calculated fixed price only after confirming the RHEL version, number of sources, expected daily log volume, ports/protocols, retention period, dashboard platform and access requirements. The estimate assumes one RHEL server, up to 25 sources, up to five listening ports, a Grafana dashboard and no high-availability cluster.

## Work Breakdown
WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE
WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE | WORK BREAKDOWN STRUCTURE
ID | Phase / Deliverable | Detailed Scope | Hours | Dependencies | Output | Status | Owner
1 | Discovery and solution design | Confirm RHEL version, sources, ports, protocols, log volume, retention, storage and dashboard requirements. | 8 | Client requirements and access | Approved design and implementation plan | Planned | Consultant
2 | RHEL and syslog-ng installation | Install packages; configure service startup, firewall, SELinux and baseline directories; validate syntax and service health. | 8 | RHEL admin access and repository | Working syslog-ng service | Planned | Consultant
3 | Listeners and routing | Configure approved TCP/UDP listeners and route messages based on listener, source IP and date. | 12 | Port and protocol list | Listener and routing configuration | Planned | Consultant
4 | Local storage structure | Create separate log paths by port and source; apply permissions, ownership and disk protection controls. | 8 | Storage mounted and sized | Structured local log repository | Planned | Consultant
5 | Rotation, compression and cleanup | Configure rotation, gzip compression, archive movement, retention and safe deletion testing. | 8 | Retention policy approved | Automated archive lifecycle | Planned | Consultant
6 | Activity history database | Maintain source IP, listener port, protocol, first/last received time and message counters. | 12 | Database option approved | Searchable source-activity history | Planned | Consultant
7 | Graphical monitoring | Build dashboard for message volume, source status, port traffic, disk use and last-received time; add inactivity alert rules. | 12 | Grafana/metrics access | Operational dashboard and alerts | Planned | Consultant
8 | Testing and tuning | Test every listener and source path; validate rotation/deletion; check performance and failure handling. | 6 | Representative test sources | Test evidence and issue log | Planned | Consultant
9 | Documentation and handover | Deliver architecture, configuration, runbook, rollback, troubleshooting and knowledge-transfer session. | 6 | Client technical contact | Documentation and handover | Planned | Consultant
TOTAL ESTIMATED HOURS |  |  | 80

## Pricing Calculator
PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR
PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR | PRICING CALCULATOR
EDITABLE BID INPUTS — YELLOW CELLS | EDITABLE BID INPUTS — YELLOW CELLS | EDITABLE BID INPUTS — YELLOW CELLS | PACKAGE COMPARISON | PACKAGE COMPARISON | PACKAGE COMPARISON
Hourly rate | 40 |  | Package | Approx. hours | Use case
Contingency | 10% |  | Proof of Concept | 32 | Two sources, two ports, basic local storage and demonstration dashboard
Working hours per day | 8 |  | Production Standard | 80 | All stated deliverables for one RHEL server; recommended bid basis
Currency | USD |  | Production Plus | 120 | Adds TLS, extended alerting, backup integration and more rigorous hardening/tuning
CALCULATION | CALCULATION | CALCULATION | CALCULATION | CALCULATION | CALCULATION
Item | Value
Base labor | 3200
Contingency amount | 320
Proposed fixed-price bid | 3520
Total estimated hours | 80
Estimated working days | 10
Effective rate after contingency | 44
Recommended Upwork bid | 3550

## Milestones
PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES
PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES | PROPOSED UPWORK MILESTONES
Milestone | Description | Hours | % of Hours | Amount | Target Day | Client Approval | Evidence
M1 | Discovery, design and approved implementation plan | 8 | 10% | 355 | 2 | Required | Design and configuration plan
M2 | Syslog-ng installation, listeners, routing and structured storage | 28 | 35% | 1242.5 | 6 | Required | Service validation and test logs
M3 | Rotation, compression, retention and activity-history database | 20 | 25% | 887.5 | 9 | Required | Archive test and history records
M4 | Dashboard, alerts, testing and performance validation | 18 | 22.5% | 798.75 | 11 | Required | Dashboard and test report
M5 | Documentation, handover and final acceptance | 6 | 7.5% | 266.25 | 12 | Required | Runbook and knowledge transfer
TOTAL |  | 80 | 100% | 3550

## Assumptions & Questions
ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS
ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS | ASSUMPTIONS AND CLIENT QUESTIONS
ESTIMATE ASSUMPTIONS | ESTIMATE ASSUMPTIONS | ESTIMATE ASSUMPTIONS | ESTIMATE ASSUMPTIONS | ESTIMATE ASSUMPTIONS | ESTIMATE ASSUMPTIONS
ID | Assumption | Impact if different
A1 | One supported RHEL server is available. | Additional servers or HA require revised effort.
A2 | Up to 25 log sources and five listening ports. | More sources/ports increase testing and dashboard work.
A3 | Client provides administrative access and approved repositories. | Access delays move the schedule.
A4 | Storage is provisioned and sized before implementation. | Storage design/procurement is outside this estimate.
A5 | Grafana may be installed or is available for dashboarding. | A different enterprise tool may require revised integration.
A6 | PostgreSQL or an approved equivalent may store activity history. | Client database standards may add configuration effort.
A7 | Retention and deletion policy is approved in writing. | Deletion will remain disabled until approval.
A8 | No custom application log parsing is included. | Custom parsers require separate analysis.
A9 | One remote knowledge-transfer session is included. | Extra sessions can be added as milestones.
QUESTIONS TO SEND BEFORE FINAL BID | QUESTIONS TO SEND BEFORE FINAL BID | QUESTIONS TO SEND BEFORE FINAL BID | QUESTIONS TO SEND BEFORE FINAL BID | QUESTIONS TO SEND BEFORE FINAL BID | QUESTIONS TO SEND BEFORE FINAL BID
# | Client Question | Why Needed | Client Answer | Confirmed? | Owner
1 | Which exact RHEL version is installed? | Package and support compatibility |  | No | Client
2 | How many sources will send logs? | Capacity and test effort |  | No | Client
3 | What is the expected daily volume or events per second? | CPU, disk and queue sizing |  | No | Client
4 | Which ports and TCP/UDP protocols are required? | Listener and firewall configuration |  | No | Client
5 | What are the active, archive and deletion retention periods? | Storage and lifecycle design |  | No | Client
6 | Is TCP/TLS required for encrypted log transport? | Security scope |  | No | Client
7 | Which graphical monitoring platform should be used? | Integration and licensing |  | No | Client
8 | When should a silent source be marked offline? | Alert thresholds |  | No | Client
9 | Is high availability or disaster recovery required? | Architecture and cost |  | No | Client
10 | What documentation and handover format is expected? | Final acceptance scope |  | No | Client

## Risks
PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS
PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS | PROJECT RISKS AND CONTROLS
ID | Risk | Probability | Impact | Score | Mitigation | Owner
R1 | Unknown log volume causes disk exhaustion | 3 | 5 | 15 | Measure traffic, size storage and configure disk alerts. | Joint
R2 | UDP packet loss results in missing logs | 3 | 4 | 12 | Use TCP/TLS for critical sources where supported. | Client
R3 | Firewall or SELinux blocks incoming messages | 3 | 3 | 9 | Pre-approve rules; validate with ss, logger and packet capture. | Joint
R4 | Incorrect retention deletes required evidence | 2 | 5 | 10 | Document approval; test rotation and deletion on sample paths first. | Joint
R5 | Source naming/IP changes break reporting | 3 | 3 | 9 | Use controlled source inventory and update process. | Client
R6 | Dashboard platform differs from assumption | 3 | 4 | 12 | Confirm monitoring platform before fixed-price commitment. | Client
R7 | Access or repository delays affect schedule | 4 | 3 | 12 | Complete access checklist before milestone start. | Client
R8 | Single-server failure interrupts collection | 2 | 5 | 10 | Document limitation; offer HA as separate scope. | Client

## Acceptance Criteria
ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST
ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST | ACCEPTANCE AND HANDOVER CHECKLIST
ID | Acceptance Criterion | Test / Evidence | Status | Client Sign-off | Notes
AC1 | Syslog-ng is active and enabled after reboot. | systemctl output and restart test | Not Started | Pending
AC2 | Every approved TCP/UDP port is listening. | ss output and connection tests | Not Started | Pending
AC3 | Logs are stored by listener port, source IP and date. | Directory and sample-message evidence | Not Started | Pending
AC4 | Rotation and compression run according to policy. | Forced rotation test and compressed file | Not Started | Pending
AC5 | Expired test archives are deleted safely. | Retention test with approved sample files | Not Started | Pending
AC6 | Dashboard shows message volume, source and port status. | Dashboard review | Not Started | Pending
AC7 | Last-received history records source IP, port and time. | Database query/report | Not Started | Pending
AC8 | Silent-source alert triggers at the approved threshold. | Controlled alert test | Not Started | Pending
AC9 | Performance and disk-protection controls are verified. | Load test and disk alert evidence | Not Started | Pending
AC10 | Configuration, runbook and handover are delivered. | Document package and session record | Not Started | Pending